## Daily Status Reports
Project Name | Project Deadline | Name of the person | Mentors | Task | Date | Remarks | Blockers
Online Game Portal | 2023-03-31 | Suma Teki | Rina Edward & Abhishek Rawal | Creating a server with express and Mongodb with API | 2023-03-16 | Created server along with routes and established database connectivity | Tried to access data from mongodb to api, but it failed.
|  |  |  | Creating Mongodb database for user login | 2023-03-17
2023-03-20
2023-03-21
2023-03-22
2023-03-23
2023-03-24
2023-03-27
2023-03-28
2023-03-29
2023-03-30
Project Name | Project Deadline | Name of the person | Mentors | Task | Date | Remarks | Blockers
Online Game Portal | 2023-03-31 | Abhilash Gudiboina | Rina Edward & Abhishek Rawal | Creating a server with Express,Mongodb with API | 2023-03-16 | Created the server along with routes,Mongodb connection | Tried to access data from api but it failed
|  |  |  | Creating mongodb database for gaming | 2023-03-17
2023-03-20
2023-03-21
2023-03-22
2023-03-23
2023-03-24
2023-03-27
2023-03-28
2023-03-29
2023-03-30
Project Name | Project Deadline | Name | Mentors | Task | Date | Remarks | Blockers
Online Game Portal | 2023-03-31 | Revanth Bolli | Rina Edward & Abhishek Rawal | User Login and Registration Pages | 2023-03-16 | completed responsive design of User login and registration pages | Tried to add extra features for login using facebook and google APIs but failed.
|  |  |  | Homepage that display the game categories and a slideshow | 2023-03-17
2023-03-20
2023-03-21
2023-03-22
2023-03-23
2023-03-24
2023-03-27
2023-03-28
2023-03-29
2023-03-30

## Project Timeline Plan
Project Name | Project Deadline | Name | Mentors | Task | Start Date | No. of days | Status
Online Game Portal | 2023-03-31 | Suma Teki | Rina Edward & Abhishek Rawal | Database creation for user detais | 2023-03-17 | 1 | In Progress
|  |  |  | Login page | 2023-03-20 | 1 | Not Started
|  |  |  | Dashboard for generating individual score | 2023-03-21 | 2 | Not Started
|  |  |  | Sort the scores of particular game and display game oreiented dashboard | 2023-03-23 | 2 | Not Started
|  |  |  | Testing with database and Improvements | 2023-03-27 | 2 | Not Started
Not Started
Not Started
Not Started
Project Name | Project Deadline | Name | Mentors | Task | Start Date | No. of days | Status
Online Game Portal | 2023-03-31 | Abhilash Gudiboina | Rina Edward & Abhishek Rawal | Database creation for gaming details | 2023-03-17 | 1 | In Progress
|  |  |  | Registration page | 2023-03-20 | 1 | Not Started
|  |  |  | Dashboard for rendering individual score from database | 2023-03-21 | 2 | Not Started
|  |  |  | Sort the scores of particular game and display game oriented dashboard | 2023-03-23 | 2 | Not Started
|  |  |  | Testing with database and improvements | 2023-03-27 | 2 | Not Started
Not Started
Not Started
Not Started
Project Name | Project Deadline | Name | Mentors | Task | Start Date | No. of days | Status
Online Game Portal | 2023-03-31 | Revanth Bolli | Rina Edward & Abhishek Rawal | User login and Registration Pages (Responsive) | 2023-03-16 | 1 | Completed
|  |  |  | Home page for displaying categories and make a slideshow | 2023-03-17 | 1 | In Progress
|  |  |  | Create Games tab to display the games and a side navigation to pick the genere. | 2023-03-20 | 2 | Not Started
|  |  |  | Create dashboard for displaying the history of games and scored points. | 2023-03-22 | 1 | Not Started
|  |  |  | Make all the pages responsive. | 2023-03-23 | 1 | Not Started
|  |  |  | Create first game. | 2023-03-24 | 2 | Not Started
|  |  |  | Create second game. | 2023-03-26 | 2 | Not Started
|  |  |  | Test the portal | 2023-03-28 | 2 | Not Started
Project Name | Project Deadline | Name | Mentors | Task | Date | No. of days | Status
Online Game Portal | 2023-03-31 | Revanth Bolli | Rina Edward & Abhishek Rawal | User login an Registration Pages (Responsive) | 2023-03-16 | 1 | Completed
|  |  |  | Home page for displaying games | 2023-03-17 | 1 | In Progress
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started

## Sheet1
Name | Task | Task Type | Tentative Date | Actual Start Date | # of Days | Status | 2023-03-16 | 2023-03-17 | 2023-03-18 | 2023-03-19 | 2023-03-20 | 2023-03-21 | 2023-03-22 | 2023-03-23 | 2023-03-24 | 2023-03-25 | 2023-03-26 | 2023-03-27 | 2023-03-28 | 2023-03-29 | 2023-03-30 | 2023-03-31
Suma | Database creation for user detais | Dev | 2023-03-17 |  | 1 | In Progress
Suma | Login page | Dev | 2023-03-20 |  | 1 | Not Started
Suma | Dashboard for generating individual score | Dev | 2023-03-21 |  | 2 | Not Started
Suma | Sort the scores of particular game and display game oreiented dashboard | Dev | 2023-03-23 |  | 2 | Not Started
Suma | Testing with database and Improvements | QA | 2023-03-27 |  | 2 | Not Started
Abhilash | Database creation for gaming details | Dev | 2023-03-17 |  | 1 | In Progress
Abhilash | Registration page | Dev | 2023-03-20 |  | 1 | Not Started
Abhilash | Dashboard for rendering individual score from database | Dev | 2023-03-21 |  | 2 | Not Started
Abhilash | Sort the scores of particular game and display game oriented dashboard | Dev | 2023-03-23 |  | 2 | Not Started
Abhilash | Testing with database and improvements | QA | 2023-03-27 |  | 2 | Not Started
Revanth | User login and Registration Pages (Responsive) | Dev | 2023-03-16 |  | 1 | Completed
Revanth | Home page for displaying categories and make a slideshow | Dev | 2023-03-17 |  | 1 | In Progress
Revanth | Create Games tab to display the games and a side navigation to pick the genere. | Dev | 2023-03-20 |  | 2 | Not Started
Revanth | Create dashboard for displaying the history of games and scored points. | Dev | 2023-03-22 |  | 1 | Not Started
Revanth | Make all the pages responsive. | Dev | 2023-03-23 |  | 1 | Not Started
Revanth | Create first game. | Dev | 2023-03-24 |  | 2 | Not Started
Revanth | Create second game. | Dev | 2023-03-26 |  | 2 | Not Started
Revanth | Test the portal | QA | 2023-03-28 |  | 2 | Not Started